## Slide 1: Multnomah County
West Hills Road Projects Update
October 8, 2018
Skyline Elementary School
MULTNOMAH COUNTY
Mike Pullen
Carrie Warren
Storm Beck
Alma Pradeepan
MURRAYSMITH
Gabe Crop
Tyler Nord
NW Germantown Rd.
NW Newberry Rd.
NW Cornelius Pass Rd.

## Slide 2: Agenda
NW Germantown Road Slide Repair Update
  Project description
  Schedule and traffic plan
NW Newberry Road Slide Repair Update
  Project description
  Schedule and traffic plan
NW Cornelius Pass Road Safety Improvement Update
  Jurisdiction transfer to ODOT
  Project description
  Schedule and traffic plans
Questions / Comments
Notes: JD

## Slide 3: NW GERMANTOWN ROAD // Slide Location and Damage Description
Project Location
13766 NW Germantown Rd.
Between Skyline Blvd. & Kaiser Rd.
Project Description
Failed culvert
Undermined slope on downhill side
Loss of shoulder

## Slide 4: NW GERMANTOWN ROAD // Repair Plan
Project Plan
Close road
Replace culvert
  Increase diameter from 18 to 36 inches
  Include erosion control rocks at either end
Repair slope
Realign road away from slide

## Slide 5: NW GERMANTOWN ROAD // Repair Schedule and Alternate Routes
Construction Schedule
7-day road closure
Mid-October, 2018
Traffic Plan
Road too narrow to keep open during repairs
Close to through traffic from Skyline to Kaiser
Alternate routes: Skyline and Springville
Access maintained for residents and first responders

## Slide 6: NW Germantown Road Questions
For more information: Web: multco.us/germantown Twitter: @MultCoRoads

## Slide 7: NW NEWBERRY ROAD // Slide Location
Project Location
Near 13342 NW Newberry Rd.
Between Skyline Blvd. & US30

## Slide 8: NW NEWBERRY ROAD // Damage Description
Project Description
Large landslide undermined road following snowstorm
Road has been closed since January 2017

## Slide 9: NW NEWBERRY ROAD // Repair Plan
Project Plan
Road will remain closed to all users
Temporary water management
Retaining wall contain all weather backfill
Rebuild and pave road

## Slide 10: NW NEWBERRY ROAD // Repair Plan
Example of reinforced retaining wall to be used in project
Example of Hot-Dip Galvanized Welded Wire Wall. Photo of the Hilfiker Retaining Wall at Evergreen Road Bridge Replacement. Photo Source: http://projects.hilfiker.com/WWW/i-tkrF7zT/

## Slide 11: NW NEWBERRY ROAD // Repair Schedule and Alternate Routes
Construction Schedule
Work begins November 2018 after Germantown
Road open to traffic late March 2019
Final paving in May 2019
Traffic Plan
Road to remain closed during construction
Local traffic will have access up to slide area on both sides
NW Cornelius Pass used as alternate route

## Slide 12: NW Newberry Road Questions
For more information: Web: multco.us/newberry Twitter: @MultCoRoads

## Slide 13: NW CORNELIUS PASS ROAD // Jurisdictional Transfer
Cornelius Pass Road Transfer
HB2017 transfers Cornelius Pass Road between US26 and US30 from Washington and Multnomah Counties to ODOT
Timing of transfer will be after completion of current project, no firm date yet
ODOT is currently gathering information about the road
Multnomah County in process of sharing available information

## Slide 14: NW CORNELIUS PASS ROAD // Project Overview
Project Description
Safety improvements are needed to Cornelius Pass Rd between Highway 30 and NW Kaiser Rd
The Oregon Legislature allocated funding to Multnomah County for the enhancements
Landslides on alternate routes delayed project

## Slide 15: NW CORNELIUS PASS ROAD // Project Overview
Corridor-Wide Improvements
Signage
Vehicle pullouts
Barriers and guardrails
Reduce pavement drop-offs with gravel shoulder wedge

## Slide 16
NW CORNELIUS PASS ROAD // Project Details and Locations
8th Ave minor curve realignment and shoulder widening
“S” curves reconstruction and realignment
Curves south of Plainview Rd signage and sight distance improvements
Kaiser Rd signage, sight distance, and shoulder widening

## Slide 17
NW CORNELIUS PASS ROAD // 2019 Construction Stages and Timelines

## Slide 18: NW CORNELIUS PASS ROAD // Stage 1 Traffic Plan

## Slide 19: NW CORNELIUS PASS ROAD // Stage 2 Traffic Plan

## Slide 20
Detour Plan
Outreach to freight, Washington and Columbia counties
Pre-construction public meeting: Spring 2019
Other issues/actions needed?
NW CORNELIUS PASS ROAD // Next Steps

## Slide 21: NW Cornelius Pass Road Questions
For more information: Web: multco.us/cornpass Twitter: @MultCoRoads