## Slide 1: Multnomah County Code Update Project
Planning Commission Meeting
September 15, 2025

## Slide 2: Presentation Agenda
Introductions
Project Update
Community Engagement Findings
Code Amendments Approach
Next Steps
Questions & Discussion

## Slide 3: Introductions
County Staff Team
Megan Gibb, Land Use Planning Director
Kevin Cook, Principal Planner
Consulting Team (MIG)
Matt Hastie
Emma-Quin Smith
Carrie Brennecke
Cathy Corliss

## Slide 4: Project Background
Project Goals
Update and modernize the Zoning Code
Make the code consistent with County policy priorities
  Promote affordable housing, social equity, climate resiliency, and customer service
Ensure housing related provisions are Clear & Objective (C&O) and comply with State legal requirements
Funded with County and State Grant Funding

## Slide 5: Overall Process
Code Audit
Policy Options & Direction
Adoption
Code Rewrite

## Slide 6: Current Project Schedule – Phases 1-2
2025 |  |  |  |  |  |  |  |  | 
JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER
PROJECT KICK-OFF
FOCUS GROUP INTERVIEWS
BEST PRACTICES RESEARCH
CODE AUDIT
KEY ISSUES REFINEMENT
COMMUNITY ENGAGEMENT
SEEKING POLICY DIRECTION
PC MEETING
BOCC MEETING

## Slide 7: Tasks Completed to Date
Project Kickoff and Goal-Setting
Meeting with Current Planning Staff
Best Practices Research
Focus Group Meetings
Code Audit Report
Summary of Key Findings
Planning Commission Briefing
Community Meetings
Refined Recommendations

## Slide 8: Code Issues
CODE ORGANIZATION
APPLICATION PROCEDURES
COMMON DEVELOPMENT STANDARDS
CONDITIONAL USES
SPECIFIC USE STANDARDS

## Slide 9: Community Engagement Process
Three in-person meetings co-hosted with neighborhood groups – Forest Park, Sauvie Island, Corbet (NEMCCA)
One hybrid meeting @ Multnomah Bldg –targeted to Ag community
Online presentations and survey – available for five weeks
Publicized via County website, interested parties list, NH associations, social media
About 120 participants in- person and 55 online

## Slide 10: Community Feedback
Code language is too complex, hard to understand and interpret
Lengthy and expensive permitting processes
Professional assistance needed for even minor applications
Lot of record and full compliance standards are significant issues
Clear & objective standards are needed; consistent interpretation lacking
Support agricultural community’s needs & opportunities
Need for customer service improvements
Improve coordination with City of Portland and NSA

## Slide 11: Refined Recommendations
Transition to 1-column format
Simplify complex explanatory narrative
Use more tables & graphics to illustrate processes and standards
Consolidate location for Permitted Land Uses for all zones via use tables
Simplify application review process and update process graphics
Consider expedited review process for certain uses
Make discretionary language clear and objective (C&O), particularly for housing

## Slide 12: Refined Recommendations
Clarify decision process for the development of housing
Consolidate definitions
Update conditional use purpose, criteria, and uses
Evaluate agri-tourism standards; coordinate with state process
Address high priority specific issues:
  Lot of record verification
  Full compliance and non-conforming situations
  Parking & other site development requirements
  Non-land use requirements (e.g., grading and erosion control)
  Accessory buildings
  Modification to approved plans
  Other short-term priority issues

## Slide 13: Next Steps: Code Amendments
Near Term
Minor accessory structures
Process for minor modifications to approved plans
Process for Agricultural Fill Permit
Process for Marijuana Business Permit
Minor amendments to Administrative Procedures
Other minor housekeeping amendments
6 Months
Lot of record verification
Nonconforming situations (uses, lots, & development)
Full compliance requirements
Long Term
Simplify code language reformat document
Reformat text to one-column
Clarify application procedures
Insert use tables for base zones
Right-size development standards
Address state administrative rules and statutes
Expand the use of graphics
Ensure requirements related to development of housing are C&O

## Slide 14: Next Steps
CONTINUE TO REFINE AMENDMENT OPTIONS BASED ON COMMISSION & COMMUNITY INPUT
BRIEF PC AND BOCC ON RESULTS
EMBARK ON PHASE 3 (CODE UPDATES) IN COORDINATION WITH STATE-FUNDED WORK

## Slide 15: Questions and Discussion

## Slide 16: Project Contact Info
Kevin Cook, Principal Planner
kevin.c.cook@multco.us
971-421-3497
Department of Community Services
Land Use Planning
1600 SE 190th Ave
Portland OR 97233